## Sheet1
2016-2017 Consolidated Budget Timeline
2016-2017 District Goal:
Outstanding Schools, Organization Efficiency, Strong Leadership, and High Quality Employees
Item# | Description of Task | Original | Revised | Actual
1 | Budget Review Committee (BRC) reviews later considerations in the 2015-2016 General Fund Budget. | N/A | 01/2009 | N/A
2 | Operations & Budget Management (OBM) drafts “Budget Calendar” memoranda and update spreadsheet and forms. OBM discuss Budget Calendar with the Senior Cabinet. | December 2015 | 2009-03-25 | 2009-03-25
3 | Senior Cabinet establishes 2016-2017 goals and objectives of the System as it relates to the Strategic Plan (SP)and District Initiatives for 2016-2017. | 2016-01-20 | 2009-04-28 | 2009-05-08
4 | OBM sends memoranda to the Senior Cabinet, providing a list of District Initiatives, emphasizing that any and all new 2016-2017 budget considerations submitted by central office, school principals, and site administrators to the Senior Cabinet must be reflective of the SP and District Initiatives for 2016-2017. The Budget Request and Efficiency forms are placed onto EBRPSS' website by OBM for staff accessibility. | 2016-01-22 | 2009-04-09 | 2009-04-27
5 | OBM offers training, as requested, for 2016-2017 budget forms. | As needed. | N/A - (As Needed) | N/A
6 | Various departmental budget managers update any and all new 2016-2017 budget considerations as well as submit to OBM their three year budget projections, using the fund balance template. Any and all new 2016-2017 major budget concerns must be noted. | 2016-02-01 | 4/2009 | 2009-04-01
7 | OBM prepares the consolidated three year budget projections based on data received from departmental budget managers. | 2016-02-05
8 | OBM presents three year budget projections to the Senior Cabinet and/or the Budget Review Committee (BRC). | 2016-02-10
9 | Senior Cabinet receives and prioritizes any and all new 2016-2017 budget considerations received from central office, school principals, and site administrators. Senior Cabinet will consider those new budget requests and efficienies submitted as recommendations to OBM. | 1/22 - 2/28/2016 | 2009-04-30 | 4/9/09 -4/27/09
10 | OBM will analyze and generate a SSB allocation for each school based on the Staffing Data actual/formulas/ratios obtained from Human Resources along with the Deputy Superintendent. | 1/30 - 2/28/2016 |  |  | 3/16 - 3/25/2016
11 | OBM compiles and consolidates any and all new 2016-2017 budget considerations submitted from the Senior Cabinet, along with new 2016-2017 budget efficiency considerations. This process generates the first draft of any and all new budget changes for the 2016-2017 complied spreadsheet created for the General Fund and all other funding sources. | by 3/15/16 | 2009-05-06 | 2009-05-06
12 | The BRC evaluates and scores the budget considerations based on three year budget projections, the SP and District Initiatives for fiscal year 2016-2017. | by 3/31/16 | 2009-05-08 | 2009-05-08
13 | The revised consolidated budget request and efficiency spreadsheet and any and three year projection updates for the entire 2016-2017 fiscal year are provided to the Deputy Superintendent for review. | 2016-04-06 | 2009-05-11 | 2009-06-01
14 | Human Resource Supervisors will schedule meetings to assist Principals in completing their 2016-2017 School Staffing Budget (SSB) and will initiate approval of any over budget request(s) of a school principals from the Chief Officer of Human Resources and the Deputy Superintendent. All over budget approvals will be forwarded to the Budget Coordinator to make budget adjustments. | 03/21 - 4/15/2016 | 2009-05-08 | 2009-05-08
15 | Superintendent meets with the BRC to review and make final recommendations for the spreadsheet to be submitted to the Board. | 3/31-/2016 | 2009-05-13 | 2009-06-05
16 | All over budget approvals will be forwarded to the Budget Coordinator to make budget adjustments, revising and/or updating a final draft of all SSB templates to be passed onto the Chief Officer of Human Resources for review who will authorized the final draft to be passed onto the Deputy Superintendent. | 2016-04-18 | 2009-05-08 | 2009-05-08 | 4/1 - 4/17/2016
17 | Schedule Board Workshop to present to Board preliminary budget considerations for any and all new budget increase and efficiencies. | 4/18- 4/28/2016
18 | OBM communicates to the Senior Cabinet and budget managers the final 2016-2017 budget considerations for the spreadsheet to be recommended by the Deputy Superintendent to the Superintendent and the Board. | by 5/4/2016 | 2009-05-14 | 2009-06-09
19 | Prior to Committee and Board approval, final 2016-2017 proposed budgets from Budget managers are submitted to OBM for review. Proposed budgets must have implemented the prioritized BRC budget considerations. The General Fund 2016-2017 Proposed Budget is to be Board approved by 6/30/2016. | 5/5-6/30/2016 | 6/1-15/09 | 2009-06-15
Note: State law requires all budgets to be Board approved by September 15th. Budgets should be within 5% of projections. Board approval is required when revenue is less and expenditures are more than 5% of projection.